## Summary
0 | 0 | 0
Phase 1 - Fundamental Modules | #REF! | #REF!
1.1 | Registration Module | Any company may request access to a custom vendor portal page by completing a simple form. Admin will have the ability to review the registration request and either 1) grant them access, creating a new vendor file in the system or 2) reject access because an existing file is already in place. In the event of #2, Admin will be able to set a temporary login credential for the vendor so that they can gain access to their existing database record.
1.2 | Licensing Module 50% COMPLETE | The ability to electronically facilitate the signature of our license agreements online. Typed signatures should have font of a signature. Almost all license agreements are templates, and therefore upon and vendor's application, they auto populate for the Admin to review and edit. The workflow is as follows: 1) vendor applies for agreement 2) vendor application auto-populates a license agreement for the admin 3) Admin reviews agreement and auto-attaches product sample images 4) If approved, Admin forwards agreement to vendor for signature 5) When signed by vendor, agreement is forwarded to client for countersignature, Client is able to view product same images 6) Once dually signed, a pdf copy of a properly-formatted agreement is sent to vendor and admin via email 7) a copy of the dually signed agreement is also stored online.
1.3 | Events Module | This is a customized calendar feature that grants the Admin the ability to: 1. post Events that are specific to a Client (for all Vendors that are licensed with the Client); 2. post events that are for specific Vendors; 3. post events that are open to all. 4. post when quarterly reports are due and when royalty fees are due.
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
1.4 | Notification Module | This is an notification system allowing the Admin to send messages to vendors, via email and/or as a notification to their homepage. All notifications send within this system are recorded in the Vendor's 'correspondence tab' of their respective CRM profile page within the Admin portal.
1.5 | ArtWork Module | Vendors should be able to view and download Client specific (high res) artwork of Clients who they are licensed with, and only view (low res) artwork of non-licensed Clients.
1.6 | Design Module | The ability for Vendors to post designs for the Admin's review. The ability for the Admin to approve, reject or deny with comments. All design decisions are both sent to the admin via email with a thumbnail image, and logged in the portal. The ability for the Admin to search and sort designs that were submitted by a particular Vendor, or search and sort designs submitted for a particular Client.
1.7 | Market-Wide Amend and Restate | Admin can create an addendum to existing agreements, select which clients the addendum applies to and, upon submission, vendors will be prompted to electronically sign the addendum. A detailed workflow of this process is availble upon request.
1.8 | One-Time Agreement Module | A one time agreement has the identical workflow as the licensing module (1.2) above. A one-time agreement just has fewer terms.
1.9 | Product Expansion (or other custom) amendment | A vendor can submit a written request for a product expansion to their existing license agreements. If approved by Admin, different product expansion amendments will be generated for each applicable client. Those amendments are signed first by the vendor, then by the client. A detailed workflow of this process is availble upon request.
0
Phase 2 Work - Creating Vendor CRM Pages & Integration with Main App | 0 | 0
2.1 | Recreating Vendor CRM pages on the AMC Admin Portal 70% COMPLETE | Recreating all the current Vendor pages: Contact, Correspondence, Operations, Action, Vendor Notes, Docs, Payments and Invoices. Include and improve upon all current functionality and content contained in existing Filemaker database, the "old system," to create new AMC admin portal
2.2 | Integrating Vendor CRM (on the AMC Admin Portal) pages with main application 100% COMPLETE | Integrate the new CRM Vendor pages of the AMC Admin Portal with the current AMC Portal, making sure all functionality of the old system is transferred to the new one. Integrate and improve upon all features and functionality from Vendor CRM pages to create main application that operates with an elegant and intuitive user interface.
2.3 | Creating better royalty fee reporting module for Vendors 10% COMPLETE | Vendors should be able to select Greek Organizations and report fees for each. Vendors should also be able to download one file with multiple worksheets that represent the different Greek Organizations. Vendors will have four options to report (based on their preferred method and the amount of transactions they must report) (1) Largest Vendors can upload detail in their own format, and just fill out summary page (2) Medium Vendors can fill out sales info per group (3) Smallest Vendors can enter sales line item by line item every day. (4) AMC can do #1 on behalf of vendors who mail in paper reports. Once quarterly report is 'submitted,' vendor receives pdf confirmation detailing sales by group and advances applied.
Phase 2 Work - Reconciling Royalty Fees, Billing, Offline Payments and Invoicing | 0 | 0
3.1 | Creating system algorithm to determine royalty fee owed by Vendor. 0% COMPLETE | When royalty fees are submitted by Vendors, the system should be able to apply royalty advances for each Greek Org and determine how much a Vendor owes for a particular Greek Org. Any outstanding advances should be carried to the next quarter. (Only after a Vendor submits royalty reports does the system compute how much they owe for each Greek Org.) Final layout should be consistent with the reporting features as described in section 2.3
3.2 | Creating bookkeeping features on the AMC Admin Portal 10% COMPLETE | * AMC Admin should be able to create invoices for any Vendor.
0 | 0 | * Allow Payments to be matched with each invoice - AMC should be able to match all payments (offline and online) to outstanding invoices and reconcile an account for a Vendor. All bookkeeping features should provide efficiencies compared to old system. Fields should auto-complete/auto-populate when possible between invoices, payments, royalty advance fields, and statements (summaries of all outstanding invoices). AMC admin should be able to access statements of activity by date range.
3.3 | Payment gateway 0% COMPLETE | Vendor should be able to provide payment for any outstanding invoice through their password protected vendor portal page. All payments will be secured with a trusted 256-bit SSL provider. The SSL certificate will secure transactions between the site and the payment gateway. Any banking information will be passed to the payment gateway and stored there. For security reasons, no banking information will be stored on the AMC web server. Any automatic recurring Vendor billing will be processed from the payment gateway. The outcomes of those transactions, whether successful or not, will be passed to the AMC website via secure API and logged against the appropriate invoice.
3.4 | Creating default triggers for invoices for each Vendor 20% COMPLETE | For each Vendor the system should auto-generate the following types of invoices:
0 | 0 | * Quarterly Royalty Fees owed for all Greek Orgs. (This will be based on the submitted Royalty Fees).
Phase 2 Work - Creating Client CRM Pages & Integration with Main App | 0 | #REF!
4.1 | Re-creating Client CRM pages on the AMC Admin Portal. 100% COMPLETE | Recreating all the current Vendor pages: Setup, Legal, Operations, Vendors, Royalty, Notes, Payments, Vendor Filter. Revisions to old structure will be necessary. Include and improve upon all current functionality and content contained in existing Filemaker database, the "old system," to create new AMC admin portal
Phase 2 Work- Database Migration | 0 | 0
5.1 | Migrating all the old data to the new structure. 60% COMPLETE | All remaining data from the old system will be uploaded to the new system. Client will advise Softura of the specific data that still need to be migrated.
5.2 | Affinity Logins 60% COMPLETE | Admin should be able to create, deactivate, and delete login credentials for Affinity team members. There should be two access levels, employee and admin. All Affinity team members should have a secure login website that is not accessible through GL.com
5.3 | Creating usernames and passwords for all Vendors 20% COMPLETE | All current Vendors will automatically have a username and password generated and emailed to them, or they will have an ability to set the aforementioned. Should they forget their credentials, there will be a secure way for them to retrieve their credentials.
5.4 | Creating usernames and passwords for all Clients 20% COMPLETE | All current Greek Organizations will automatically have a username and password generated and emailed to them, or they will have an ability to set the aforementioned. Should they forget their credentials, there will be a secure way for them to retrieve their credentials.
Phase 3 Work - Updates to GreekLicensing.com | 0 | 0
6.1 | Updating layout and design 80% COMPLETE | All functionality included in the existing GreekLicensing.com will be included in the final outcome, including but not limited to, AMC advertising banners, newsfeeds, and a sophisticated vendor search interface allowing consumers to identified licensed vendors by name, product and/or location.
6.2 | Vendor Web Profiles 40% COMPLETE | Vendors will be able to submit changes to content on their publically-viewable web profiles, including company description, vendor logo, and 10 product images. Additional product image 'slots' may be granted by the admin. All requested changes are placed in a queue for the admin to approve or reject, side-by-side with the current profile version. Any admin-typed approvals or rejections should be emailed to vendor upon submission. Any vendor-requested updates to their private contact information should be granted automatically; old versions of contact information should be auto-achieved for Admin viewing.
6.3 | Greek Org Whitelabeled Vendor Rosters 50% COMPLETE | All Greek organizations will have a searchable vendor roster, accessible by the public through greeklicensing.com. Each greek org will have two versions of their search page; the first will be with branding consistent with the GL.com site as a whole. The second will have a customizable banner and font, button, and background colors so as to be able to be placed inside a client's existing website to match Client website branding.
6.4 (same as 2.2) | Tying database driven pages to the "App" database 100% COMPLETE | All info about Greek Orgs and Vendors should come from the application database. When a vendor association is changed in the AMC admin portal a licensee will appear (and a revoked licensee will disappear) on the public page (and vendor search interface) of GL.com

## Detail (2)
Phase 1 - Fundamental Modules |  | Module | Phase | Status | Description
1.1 | Registration Module |  | Phase 1 |  | Any company may request access to a custom vendor portal page by completing a simple form. Admin will have the ability to review the registration request and either 1) grant them access, creating a new vendor file in the system or 2) reject access because an existing file is already in place. In the event of #2, Admin will be able to set a temporary login credential for the vendor so that they can gain access to their existing database record.
a | request a login | Registration Module | Phase 1 | Working | ok
b | confirmation of request email sent | Registration Module | Phase 1 | Working | ok
c | admin review panel | Registration Module | Phase 1 | Working | ok
d | admin selects decline option - redirection email | Registration Module | Phase 1 | Working | ok
e | declined vendor files are removed | Registration Module | Phase 1 |  | currently these vendor files statuses go from 'pending' to 'cancelled' - which is wrong. The files should be deleted entirely, and only viewable from Admin >registrants>Declined. If they must remain in the system they can be listed as 'Duplicate' status | 32 | When the admin rejects a regitration show only in the Declined Tab
f | admin selects aprove option - confirmation email sent | Registration Module | Phase 1 | Working | ok
g | first time registrant welcome page | Registration Module | Phase 1 |  | new feature: 'take a tour' 'help by topic' | More Details Required
1.2 | Licensing Module 50% COMPLETE |  | Phase 1 |  | The ability to electronically facilitate the signature of our license agreements online. Typed signatures should have font of a signature. Almost all license agreements are templates, and therefore upon and vendor's application, they auto populate for the Admin to review and edit. The workflow is as follows: 1) vendor applies for agreement 2) vendor application auto-populates a license agreement for the admin 3) Admin reviews agreement and auto-attaches product sample images 4) If approved, Admin forwards agreement to vendor for signature 5) When signed by vendor, agreement is forwarded to client for countersignature, Client is able to view product same images 6) Once dually signed, a pdf copy of a properly-formatted agreement is sent to vendor and admin via email 7) a copy of the dually signed agreement is also stored online.
a | admin can view and edit license agreement templates for each org under Clients > Spec. Client > Lisc Agreement Templates | Licensing Module | Phase 1 | Working | ok
b | admin can preview agreement templates | Licensing Module | Phase 1 | Working | preview button used to work, but no longer does | fixed
c | Vendor Updates info on 'profile' tab, especially contact/product info/financial info | Licensing Module | Phase 1 | Working | ok
d | Vendor applies | Licensing Module | Phase 1
e | company info | Licensing Module | Phase 1 | Working | state should auto populate | This works
f | organizations | Licensing Module | Phase 1 |  | formatting looks a little off (some names go to two lines) | 2 | Increase the width of the columns
g | proposed use | Licensing Module | Phase 1 | Working | ok - auto populates from the profile page
h | financials | Licensing Module | Phase 1 |  | ok - auto-populates but red bar at top should be gone | 2
i | checkout | Licensing Module | Phase 1 |  | ok - correct totals are shown | 2 | Need to add description text. | Need Description Text from Eli
j | pay advance by ACH | Licensing Module | Phase 1 |  | untested/never tested | More Details Required | Co-Ordinate with APH to test this | Setup meeting with Prabakar
k | pay by emailed invoice | Licensing Module | Phase 1 |  | invoice rec'd but need to be formatted, also invoice does not show in vendors invoice tab | 16 | Eli will send the sample invoice the PDF should be formated. | Ask Eli for Sample Invoice
l | Vendor provides payment | Licensing Module | Phase 1 |  | no ability for vendor to see or pay invoice | 40 | Currently it has Pay Online as link to inovice ID. IT should be added as action item, invoice link should the invoice. Also Admins should be able apply a payment. Should add a field to categorize how the payment is received, for example paid online, thru APH, etc.,
m | Vendor sends in product samples/Admin uploads to vendor 'product info tab' | Licensing Module | Phase 1 | Working | uploading does not stick | Working | Quality Sample Images are not be able to upload.
n | Vendor's quality sample images auto attach to the pending agreement | Licensing Module | Phase 1 |  | they can be added manually but they do not yet auto attach | 16 | Quality Sample images should be attached automatically
o | When payment is rec'd the 'payment rec'd' box is checked and the vendor's profile relflects the same | Licensing Module | Phase 1 |  | vendor's profile does accuratly reflects the changing statues of payment and samples, but no way to test the payment box being auto checked upon payment | More Details Required | In the License Agreement page based on the status update the check boxes Q: How do we handle the partial payments?
p | Admin can view and sort agreements that are in the queue in Vendors > Lisc. Agreements | Licensing Module | Phase 1 |  | pending agreements are shown but you can't filter by org or vendor. Also the drop-down is blank. | 16 | Add the funtionalty same as Lice. Agreements but use clients instead of vendors
q | Admin can make notes for affinity, the vendor and the client on the agreement application | Licensing Module | Phase 1 | Working | ok
r | Admin can edit contract terms | Licensing Module | Phase 1 | Working | ok
s | Admin can view and preview the agreement | Licensing Module | Phase 1 |  | preview button used to work, but no longer does | fixed | Not an issue
t | Admin approves agreement, and sends to vendor | Licensing Module | Phase 1 | Working | ok
u | Admin rejects agreement, and sends to vendor | Licensing Module | Phase 1 |  |  | Details Required
v | Vendor can view and preview the agreement | Licensing Module | Phase 1 |  | preview button used to work, but no longer does | fixed
w | Vendor signs and agrees to contract | Licensing Module | Phase 1 |  | title should be below name in the signature field. Font should look more like a signature. | On screen its possible to show the Singnature kind font. On PDF its not possible | Not an issue. Switch the title and sign in the order. Sign should appear first and then the title column.
x | once vendor signs - agreement status should be 'awaiting client signature' | Licensing Module | Phase 1 |  | the status is correct, but the vendor should not be able to view the agreement under the 'action' tab | More Details Required | When the Status is Awaiting Client Signature hide the view button from the action column
y | once vendor signs, the client is notified via email that an agreement is waiting | Licensing Module | Phase 1 | Working | ok
z | cleint contact preferences | Licensing Module | Phase 1 |  | in the client profile there needs to be an email field designated as the contact for agreement countersignatures | 24 | Add new field and send the license agreement emails to this address.
aa | Vendor refuses to sign contract | Licensing Module | Phase 1
bb | Vendor-signed contract goes to client for review | Licensing Module | Phase 1 | Working | ok
cc | Client can view agreement, terms, product samples and reccomendation | Licensing Module | Phase 1 | Working | ok
dd | Client can view and preview the agreement | Licensing Module | Phase 1 |  | preview button used to work, but no longer does. Agreement has lost it's formatting as well. | 4 | Remove the border that appears around the PDF
ee | If client rejects, then email is sent to affinity | Licensing Module | Phase 1
ff | If client approves, a copy is stored and a copy is emailed to Affinity and vendor | Licensing Module | Phase 1 |  | a pdf copy is not emailed to admin and vendor. When client views the dually signed agreement in their profile it has lost all formatting and cannot preview via pdf. Also when client clicks 'submit signature' nothing happens on the page. | 8 | Make sure the email works and the profile page should be view only page
gg | the dually signed agreement is viewable from both client, affinity and vendor profiles | Licensing Module | Phase 1 |  | dually signed agreements are not yet viewable by client, and have lost their formatting in both the vendor and admin views. | 2 | Remove the border that appears around the PDF
hh | once a vendor is licensed with at least one client, their status should go from 'registered' to 'current' | Licensing Module | Phase 1 |  | currently the vendor status remains as 'registered' | 8
1.3 | Events Module |  | Phase 1 |  | This is a customized calendar feature that grants the Admin the ability to: 1. post Events that are specific to a Client (for all Vendors that are licensed with the Client); 2. post events that are for specific Vendors; 3. post events that are open to all. 4. post when quarterly reports are due and when royalty fees are due.
a | admin can post, edit, and remove events for select vendors and clients | Events Module | Phase 1 | Working | ok
b | client can request an event posting | Events Module | Phase 1 |  | basic form - title, date, location, description on the client's 'events' tab | More Details Required
c | post event for all vendors of a client | Events Module | Phase 1 | Working | ok
d | post event for all licensed vendors | Events Module | Phase 1 | Working | ok
e | post event for select vendors | Events Module | Phase 1 | Working | ok
f | post event for select clients | Events Module | Phase 1 | Working | ok
g | post event for all clients | Events Module | Phase 1 | Working | ok
1.4 | Notification Module |  | Phase 1 |  | This is an notification system allowing the Admin to send messages to vendors, via email and/or as a notification to their homepage. All notifications send within this system are recorded in the Vendor's 'correspondence tab' of their respective CRM profile page within the Admin portal.
a | admin can post, edit, and remove notifications for select vendors and clients | Notification Module | Phase 1 | Working | ok
b | admin can view past notifications by filters | Notification Module | Phase 1 |  | looking for basic filters on the admin page that lists all sent notifications | More Details Required
c | messages can be sent from email and/or site notification | Notification Module | Phase 1 |  | site notifications are posted but emails are not yet sent to either vendors or clients | More Details Required
d | messages are copied in the correspondence tab of recipents | Notification Module | Phase 1 |  | messages are copied to a single vendors' correspondence tab, but not yet for clients | More Details Required
e | send message for all vendors of a client | Notification Module | Phase 1 |  | messages are posted to each vendor's profile page, but they are not yet copied to the vendors' correspondence tab | More Details Required
f | send message for all vendors | Notification Module | Phase 1 |  | messages are posted to each vendor's profile page, but they are not yet copied to the vendors' correspondence tab | More Details Required
g | all vendors' should be subdivided by vendor status (current, illegal etc) | Notification Module | Phase 1 |  | missing feature | More Details Required
h | send message for select vendors | Notification Module | Phase 1 |  | messages are posted to the vendor's profile page,AND are yet copied to the vendors' correspondence tab
i | send message for select clients | Notification Module | Phase 1 |  | messages are posted to each client's profile page, but they are not yet copied to the clients' correspondence tab | More Details Required
j | send message for all clients | Notification Module | Phase 1 |  | messages are posted to each client's profile page, AND copied to each clients' correspondence tab
k | vendors can view messages from their profiles | Notification Module | Phase 1 |  | admin is able to post the message, however the message formatting shows the html in the vendor's profile if the vendor is trying to view it
l | clients can view messages from their profiles | Notification Module | Phase 1 | Working | ok
m | recipeint can view message when they click on the notification tab link in their profile | Notification Module | Phase 1 |  | small bug - when the preview is clicked nothing happens. If you go to all notificaitons, then click on the message, it does open however.
1.5 | ArtWork Module |  | Phase 1 |  | Vendors should be able to view and download Client specific (high res) artwork of Clients who they are licensed with, and only view (low res) artwork of non-licensed Clients.
a | admin can edit, delete, and upload offical artwork | ArtWork Module | Phase 1 | Working | ok
b | client can delete and upload offical artwork | ArtWork Module | Phase 1 |  | client upload button has typo "Artworks". Client cannot upload the necceary filetypes. Client has an edit and delete button but they do not work. | fixed edit and delete button, is the typo the extra 's' on the end and what types need to be uploaded?
c | artwork appears as thumbnails where possible | ArtWork Module | Phase 1 |  | thumbnails of artwork do not yet appear (for client, vendor and admin) but placeholder images for filetypes that cannot be converted to thumbnail do appear however | some filetypes cannot be viewed in the browser what filetypes would you like to see thumbnails for? |  | also some previus data seems to be incorrect
d | vendor can preview but not download unlicensed art | ArtWork Module | Phase 1 |  | vendor cannot preview art work yet - however they are appropriately prevented from downloading artwork for clients they are not yet licensed with |  |  | System currently points to missing files need to find disconnect and remedy
e | vendor can preview AND download licensed art | ArtWork Module | Phase 1 |  | vendor cannot preview art work yet - however they CAN appropriately download artwork for clients they are licensed with
1.6 | Design Module |  | Phase 1 |  | The ability for Vendors to post designs for the Admin's review. The ability for the Admin to approve, reject or deny with comments. All design decisions are both sent to the admin via email with a thumbnail image, and logged in the portal. The ability for the Admin to search and sort designs that were submitted by a particular Vendor, or search and sort designs submitted for a particular Client.
a | vendor can upload designs | Design Module | Phase 1 | Working | ok
b | add files' button goes away after limit is reached | Design Module | Phase 1 |  | should gray-out once 5 images (the max) have been reached
c | designs approval email can be set by vendor | Design Module | Phase 1 |  | new feature: there needs to be a field in a vendor's profile to be the destination of designs emails. Right now they are all going to the recovery email address
d | admin review panel, able to approve/reject | Design Module | Phase 1 | Working | ok
e | confirmation of approval email sent to vendor | Design Module | Phase 1 | Working | ok
f | confirmation of rejection email sent to vendor | Design Module | Phase 1 | Working | ok
g | approved & rejected designs and tags are stored | Design Module | Phase 1 |  | the "tag field" is not stored and shows as blank
h | admin can search/filter old approved & rejected designs | Design Module | Phase 1 |  | fatal error' occurs when filtering rejected, approved designs
i | 'admin can click and view old approved & rejected designs | Design Module | Phase 1 |  | when admin clicks on a thumbnail, the pop up window goes to the top left image
1.7 | Market-Wide Amend and Restate |  | Phase 1 |  | Admin can create an addendum to existing agreements, select which clients the addendum applies to and, upon submission, vendors will be prompted to electronically sign the addendum. A detailed workflow of this process is availble upon request. | More Details Required
1.8 | One-Time Agreement Module |  | Phase 1 |  | A one time agreement has the identical workflow as the licensing module (1.2) above. A one-time agreement just has fewer terms. | More Details Required
1.9 | Product Expansion (or other custom) amendment |  | Phase 1 |  | A vendor can submit a written request for a product expansion to their existing license agreements. If approved by Admin, different product expansion amendments will be generated for each applicable client. Those amendments are signed first by the vendor, then by the client. A detailed workflow of this process is availble upon request. | More Details Required

## Detail
Issue Fix Status
Phase 1 - Fundamental Modules |  | Module | Phase | Status | Description
1.1 | Registration Module |  | Phase 1 |  | Any company may request access to a custom vendor portal page by completing a simple form. Admin will have the ability to review the registration request and either 1) grant them access, creating a new vendor file in the system or 2) reject access because an existing file is already in place. In the event of #2, Admin will be able to set a temporary login credential for the vendor so that they can gain access to their existing database record.
a | request a login | Registration Module | Phase 1 | Working | ok
b | confirmation of request email sent | Registration Module | Phase 1 | Working | ok
c | admin review panel | Registration Module | Phase 1 | Working | ok
d | admin selects decline option - redirection email | Registration Module | Phase 1 | Working | ok
e | declined vendor files are removed | Registration Module | Phase 1 |  | currently these vendor files statuses go from 'pending' to 'cancelled' - which is wrong. The files should be deleted entirely, and only viewable from Admin >registrants>Declined. If they must remain in the system they can be listed as 'Duplicate' status | Fixed
f | admin selects aprove option - confirmation email sent | Registration Module | Phase 1 | Working | ok
g | first time registrant welcome page | Registration Module | Phase 1 |  | new feature: 'take a tour' 'help by topic' | Waiting on Eli
1.2 | Licensing Module 50% COMPLETE |  | Phase 1 |  | The ability to electronically facilitate the signature of our license agreements online. Typed signatures should have font of a signature. Almost all license agreements are templates, and therefore upon and vendor's application, they auto populate for the Admin to review and edit. The workflow is as follows: 1) vendor applies for agreement 2) vendor application auto-populates a license agreement for the admin 3) Admin reviews agreement and auto-attaches product sample images 4) If approved, Admin forwards agreement to vendor for signature 5) When signed by vendor, agreement is forwarded to client for countersignature, Client is able to view product same images 6) Once dually signed, a pdf copy of a properly-formatted agreement is sent to vendor and admin via email 7) a copy of the dually signed agreement is also stored online.
a | admin can view and edit license agreement templates for each org under Clients > Spec. Client > Lisc Agreement Templates | Licensing Module | Phase 1 | Working | ok
b | admin can preview agreement templates | Licensing Module | Phase 1 |  | preview button used to work, but no longer does | fixed
c | Vendor Updates info on 'profile' tab, especially contact/product info/financial info | Licensing Module | Phase 1 | Working | ok
d | Vendor applies | Licensing Module | Phase 1
e | company info | Licensing Module | Phase 1 |  | state should auto populate | Fixed
f | organizations | Licensing Module | Phase 1 |  | formatting looks a little off (some names go to two lines) | Fixed
g | proposed use | Licensing Module | Phase 1 |  | ok - auto populates from the profile page
h | financials | Licensing Module | Phase 1 |  | ok - auto-populates but red bar at top should be gone | Fixed
i | checkout | Licensing Module | Phase 1 |  | ok - correct totals are shown
j | pay advance by ACH | Licensing Module | Phase 1 |  | untested/never tested
k | pay by emailed invoice | Licensing Module | Phase 1 |  | invoice rec'd but need to be formatted, also invoice does not show in vendors invoice tab | Fixed
l | Vendor provides payment | Licensing Module | Phase 1 |  | no ability for vendor to see or pay invoice
m | Vendor sends in product samples/Admin uploads to vendor 'product info tab' | Licensing Module | Phase 1 |  | uploading does not stick | Fixed
n | Vendor's quality sample images auto attach to the pending agreement | Licensing Module | Phase 1 |  | they can be added manually but they do not yet auto attach | Fixed
o | When payment is rec'd the 'payment rec'd' box is checked and the vendor's profile relflects the same | Licensing Module | Phase 1 |  | vendor's profile does accuratly reflects the changing statues of payment and samples, but no way to test the payment box being auto checked upon payment
p | Admin can view and sort agreements that are in the queue in Vendors > Lisc. Agreements | Licensing Module | Phase 1 |  | pending agreements are shown but you can't filter by org or vendor. Also the drop-down is blank. | Fixed
q | Admin can make notes for affinity, the vendor and the client on the agreement application | Licensing Module | Phase 1 | Working | ok
r | Admin can edit contract terms | Licensing Module | Phase 1 | Working | ok
s | Admin can view and preview the agreement | Licensing Module | Phase 1 |  | preview button used to work, but no longer does | Fixed
t | Admin approves agreement, and sends to vendor | Licensing Module | Phase 1 | Working | ok
u | Admin rejects agreement, and sends to vendor | Licensing Module | Phase 1
v | Vendor can view and preview the agreement | Licensing Module | Phase 1 |  | preview button used to work, but no longer does | Fixed
w | Vendor signs and agrees to contract | Licensing Module | Phase 1 |  | title should be below name in the signature field. Font should look more like a signature. | Fixed
x | once vendor signs - agreement status should be 'awaiting client signature' | Licensing Module | Phase 1 |  | the status is correct, but the vendor should not be able to view the agreement under the 'action' tab | Fixed
y | once vendor signs, the client is notified via email that an agreement is waiting | Licensing Module | Phase 1 | Working | ok
z | cleint contact preferences | Licensing Module | Phase 1 |  | in the client profile there needs to be an email field designated as the contact for agreement countersignatures
aa | Vendor refuses to sign contract | Licensing Module | Phase 1
bb | Vendor-signed contract goes to client for review | Licensing Module | Phase 1 | Working | ok
cc | Client can view agreement, terms, product samples and reccomendation | Licensing Module | Phase 1 | Working | ok
dd | Client can view and preview the agreement | Licensing Module | Phase 1 |  | preview button used to work, but no longer does. Agreement has lost it's formatting as well. | Fixed
ee | If client rejects, then email is sent to affinity | Licensing Module | Phase 1
ff | If client approves, a copy is stored and a copy is emailed to Affinity and vendor | Licensing Module | Phase 1 |  | a pdf copy is not emailed to admin and vendor. When client views the dually signed agreement in their profile it has lost all formatting and cannot preview via pdf. Also when client clicks 'submit signature' nothing happens on the page. | FIxed
gg | the dually signed agreement is viewable from both client, affinity and vendor profiles | Licensing Module | Phase 1 |  | dually signed agreements are not yet viewable by client, and have lost their formatting in both the vendor and admin views. | Fixed
hh | once a vendor is licensed with at least one client, their status should go from 'registered' to 'current' | Licensing Module | Phase 1 |  | currently the vendor status remains as 'registered' | Fixed
1.3 | Events Module |  | Phase 1 |  | This is a customized calendar feature that grants the Admin the ability to: 1. post Events that are specific to a Client (for all Vendors that are licensed with the Client); 2. post events that are for specific Vendors; 3. post events that are open to all. 4. post when quarterly reports are due and when royalty fees are due.
a | admin can post, edit, and remove events for select vendors and clients | Events Module | Phase 1 | Working | ok
b | client can request an event posting | Events Module | Phase 1 |  | basic form - title, date, location, description on the client's 'events' tab
c | post event for all vendors of a client | Events Module | Phase 1 | Working | ok
d | post event for all licensed vendors | Events Module | Phase 1 | Working | ok
e | post event for select vendors | Events Module | Phase 1 | Working | ok
f | post event for select clients | Events Module | Phase 1 | Working | ok
g | post event for all clients | Events Module | Phase 1 | Working | ok
1.4 | Notification Module |  | Phase 1 |  | This is an notification system allowing the Admin to send messages to vendors, via email and/or as a notification to their homepage. All notifications send within this system are recorded in the Vendor's 'correspondence tab' of their respective CRM profile page within the Admin portal.
a | admin can post, edit, and remove notifications for select vendors and clients | Notification Module | Phase 1 | Working | ok
b | admin can view past notifications by filters | Notification Module | Phase 1 |  | looking for basic filters on the admin page that lists all sent notifications
c | messages can be sent from email and/or site notification | Notification Module | Phase 1 |  | site notifications are posted but emails are not yet sent to either vendors or clients | Fixed
d | messages are copied in the correspondence tab of recipents | Notification Module | Phase 1 |  | messages are copied to a single vendors' correspondence tab, but not yet for clients | Fixed
e | send message for all vendors of a client | Notification Module | Phase 1 |  | messages are posted to each vendor's profile page, but they are not yet copied to the vendors' correspondence tab | Fixed
f | send message for all vendors | Notification Module | Phase 1 |  | messages are posted to each vendor's profile page, but they are not yet copied to the vendors' correspondence tab | Fixed
g | all vendors' should be subdivided by vendor status (current, illegal etc) | Notification Module | Phase 1 |  | missing feature
h | send message for select vendors | Notification Module | Phase 1 | Working | messages are posted to the vendor's profile page,AND are yet copied to the vendors' correspondence tab
i | send message for select clients | Notification Module | Phase 1 |  | messages are posted to each client's profile page, but they are not yet copied to the clients' correspondence tab | Fixed
j | send message for all clients | Notification Module | Phase 1 | Working | messages are posted to each client's profile page, AND copied to each clients' correspondence tab
k | vendors can view messages from their profiles | Notification Module | Phase 1 |  | admin is able to post the message, however the message formatting shows the html in the vendor's profile if the vendor is trying to view it | Fixed
l | clients can view messages from their profiles | Notification Module | Phase 1 | Working | ok
m | recipeint can view message when they click on the notification tab link in their profile | Notification Module | Phase 1 |  | small bug - when the preview is clicked nothing happens. If you go to all notificaitons, then click on the message, it does open however. | Fixed
1.5 | ArtWork Module |  | Phase 1 |  | Vendors should be able to view and download Client specific (high res) artwork of Clients who they are licensed with, and only view (low res) artwork of non-licensed Clients.
a | admin can edit, delete, and upload offical artwork | ArtWork Module | Phase 1 | Working | ok
b | client can delete and upload offical artwork | ArtWork Module | Phase 1 |  | client upload button has typo "Artworks". Client cannot upload the necceary filetypes. Client has an edit and delete button but they do not work. | Fixed
c | artwork appears as thumbnails where possible | ArtWork Module | Phase 1 |  | thumbnails of artwork do not yet appear (for client, vendor and admin) but placeholder images for filetypes that cannot be converted to thumbnail do appear however | Fixed | also some previus data seems to be incorrect
d | vendor can preview but not download unlicensed art | ArtWork Module | Phase 1 |  | vendor cannot preview art work yet - however they are appropriately prevented from downloading artwork for clients they are not yet licensed with | Fixed | System currently points to missing files need to find disconnect and remedy
e | vendor can preview AND download licensed art | ArtWork Module | Phase 1 |  | vendor cannot preview art work yet - however they CAN appropriately download artwork for clients they are licensed with | Fixed | System currently points to missing files need to find disconnect and remedy
1.6 | Design Module |  | Phase 1 |  | The ability for Vendors to post designs for the Admin's review. The ability for the Admin to approve, reject or deny with comments. All design decisions are both sent to the admin via email with a thumbnail image, and logged in the portal. The ability for the Admin to search and sort designs that were submitted by a particular Vendor, or search and sort designs submitted for a particular Client.
a | vendor can upload designs | Design Module | Phase 1 | Working | ok
b | add files' button goes away after limit is reached | Design Module | Phase 1 |  | should gray-out once 5 images (the max) have been reached | 4 Hrs | This is not possible
c | designs approval email can be set by vendor | Design Module | Phase 1 |  | new feature: there needs to be a field in a vendor's profile to be the destination of designs emails. Right now they are all going to the recovery email address
d | admin review panel, able to approve/reject | Design Module | Phase 1 | Working | ok
e | confirmation of approval email sent to vendor | Design Module | Phase 1 | Working | ok
f | confirmation of rejection email sent to vendor | Design Module | Phase 1 | Working | ok
g | approved & rejected designs and tags are stored | Design Module | Phase 1 |  | the "tag field" is not stored and shows as blank
h | admin can search/filter old approved & rejected designs | Design Module | Phase 1 |  | fatal error' occurs when filtering rejected, approved designs | Fixed
i | 'admin can click and view old approved & rejected designs | Design Module | Phase 1 |  | when admin clicks on a thumbnail, the pop up window goes to the top left image | Fixed
1.7 | Market-Wide Amend and Restate |  | Phase 1 |  | Admin can create an addendum to existing agreements, select which clients the addendum applies to and, upon submission, vendors will be prompted to electronically sign the addendum. A detailed workflow of this process is availble upon request.
1.8 | One-Time Agreement Module |  | Phase 1 |  | A one time agreement has the identical workflow as the licensing module (1.2) above. A one-time agreement just has fewer terms.
1.9 | Product Expansion (or other custom) amendment |  | Phase 1 |  | A vendor can submit a written request for a product expansion to their existing license agreements. If approved by Admin, different product expansion amendments will be generated for each applicable client. Those amendments are signed first by the vendor, then by the client. A detailed workflow of this process is availble upon request.
Phase 2 Work - Creating Vendor CRM Pages & Integration with Main App
2.1 | Recreating Vendor CRM pages on the AMC Admin Portal 70% COMPLETE |  |  |  | Recreating all the current Vendor pages: Contact, Correspondence, Operations, Action, Vendor Notes, Docs, Payments and Invoices. Include and improve upon all current functionality and content contained in existing Filemaker database, the "old system," to create new AMC admin portal
a | Recreate data fields |  |  |  | 80% tabs and data fields are recreated - most incomplete sections are "payments" and "invoices" | On Going Task
b | Include and improve upon existing functionality |  |  |  | Assorted bugs still exist - too varied to list here but we can detail these however your prefer | Fixed
2.2 | Integrating Vendor CRM (on the AMC Admin Portal) pages with main application 100% COMPLETE |  |  |  | Integrate the new CRM Vendor pages of the AMC Admin Portal with the current AMC Portal, making sure all functionality of the old system is transferred to the new one. Integrate and improve upon all features and functionality from Vendor CRM pages to create main application that operates with an elegant and intuitive user interface.
a | Backend database drives the content on the public webpage www.greeklicensing.com |  |  |  | The framework seems to be in place. Once a change is made to a vendor's status or information, that change appears to be reflected on the public website
2.3 | Creating better royalty fee reporting module for Vendors 10% COMPLETE |  |  |  | Vendors should be able to select Greek Organizations and report fees for each. Vendors should also be able to download one file with multiple worksheets that represent the different Greek Organizations. Vendors will have four options to report (based on their preferred method and the amount of transactions they must report) (1) Largest Vendors can upload detail in their own format, and just fill out summary page (2) Medium Vendors can fill out sales info per group (3) Smallest Vendors can enter sales line item by line item every day. (4) AMC can do #1 on behalf of vendors who mail in paper reports. Once quarterly report is 'submitted,' vendor receives pdf confirmation detailing sales by group and advances applied.
a | Option 1 - a vendor should be able to fill out a form |  |  |  | 0% functional. Vendor cannot add more than one line item when reporting by sale. No way to submit report, have an invoice generated, or pay for royalties. | Fixed
b | Option 2 - a vendor can download a template and upload it back online |  |  |  | 0% functional. Vendor can upload complete templates, but cannot fill out a summary page, generate an invoice or pay their royalties. | Fixed
c | Option 3 - a vendor can upload their own report (word, excel, pdf etc) |  |  |  | 0% functional. Vendor can upload a file, but cannot fill out a summary page, generate an invoice or pay their royalties. | Fixed
d | The reporting process should be free of bugs |  |  |  | uploading reports results in false error messages | Fixed
e | The reporting process should be intuitive |  |  |  | The current quarter and FY should be the default value when submitting a report | Fixed
f | Final submission should generate an invoice and the ability for the vendor to pay at that time |  |  |  | does not exist yet | Fixed
Phase 2 Work - Reconciling Royalty Fees, Billing, Offline Payments and Invoicing
3.1 | Creating system algorithm to determine royalty fee owed by Vendor. 0% COMPLETE |  |  |  | When royalty fees are submitted by Vendors, the system should be able to apply royalty advances for each Greek Org and determine how much a Vendor owes for a particular Greek Org. Any outstanding advances should be carried to the next quarter. (Only after a Vendor submits royalty reports does the system compute how much they owe for each Greek Org.) Final layout should be consistent with the reporting features as described in section 2.3 | 5/29/13 Jason will complete it
a | Reports should generate a summary page that deducts any remaining advaces (if applicable) |  |  |  | does not exist yet - previous development company could not figure out how to do this | Fixed
3.2 | Creating bookkeeping features on the AMC Admin Portal 10% COMPLETE |  |  |  | * AMC Admin should be able to create invoices for any Vendor.
* Allow Payments to be matched with each invoice - AMC should be able to match all payments (offline and online) to outstanding invoices and reconcile an account for a Vendor. All bookkeeping features should provide efficiencies compared to old system. Fields should auto-complete/auto-populate when possible between invoices, payments, royalty advance fields, and statements (summaries of all outstanding invoices). AMC admin should be able to access statements of activity by date range.
a | Bookkeeping features that track payments against invoices |  |  |  | tabs exist but do not have functionality beyond the very basic
b | Bookkeeping feaures that allow reports to be run on accounts receivable and accounts payable |  |  |  | does not exist yet
3.3 | Payment gateway 0% COMPLETE |  |  |  | Vendor should be able to provide payment for any outstanding invoice through their password protected vendor portal page. All payments will be secured with a trusted 256-bit SSL provider. The SSL certificate will secure transactions between the site and the payment gateway. Any banking information will be passed to the payment gateway and stored there. For security reasons, no banking information will be stored on the AMC web server. Any automatic recurring Vendor billing will be processed from the payment gateway. The outcomes of those transactions, whether successful or not, will be passed to the AMC website via secure API and logged against the appropriate invoice.
a | Untested |  |  |  | We have established a partnership with Automated Payment Highway (Billhighway) but this feature has not yet been tested | 32 Hrs - Jason
3.4 | Creating default triggers for invoices for each Vendor 20% COMPLETE |  |  |  | For each Vendor the system should auto-generate the following types of invoices:
* Quarterly Royalty Fees owed for all Greek Orgs. (This will be based on the submitted Royalty Fees).
a | Mass invoices for annual fees and late fees - auto customized per vendor |  |  |  | untested | Need to ask Eli
b | individual invoices autogenerated for roylaties due, when a vendor submits a quarterly report |  |  |  | does not exist yet | Need to ask Eli
c | miscellaneous invoices can be made manually by admin - and sent to vendor |  |  |  | manual invoices can be generated and sent to vendors via email
Phase 2 Work - Creating Client CRM Pages & Integration with Main App |  |  |  |  | #REF!
4.1 | Re-creating Client CRM pages on the AMC Admin Portal. 100% COMPLETE |  |  |  | Recreating all the current Vendor pages: Setup, Legal, Operations, Vendors, Royalty, Notes, Payments, Vendor Filter. Revisions to old structure will be necessary. Include and improve upon all current functionality and content contained in existing Filemaker database, the "old system," to create new AMC admin portal
| Recreate data fields |  |  |  | All fields appear to be recreated and merged correctly
Phase 2 Work- Database Migration
5.1 | Migrating all the old data to the new structure. 60% COMPLETE |  |  |  | All remaining data from the old system will be uploaded to the new system. Client will advise Softura of the specific data that still need to be migrated.
a | Data has been partially migrated |  |  |  | Filemaker Tabs that remain to be updated to the Gateway include: 'Clients' 'Agreements' 'Payments' and 'Invoices'
5.2 | Affinity Logins 60% COMPLETE |  |  |  | Admin should be able to create, deactivate, and delete login credentials for Affinity team members. There should be two access levels, employee and admin. All Affinity team members should have a secure login website that is not accessible through GL.com
a | Admin can create, deactive, and delete employee logins |  |  |  | admin can create, and deactivate, but cannot delete | Fixed
b | each user has one of two access levels |  |  |  | currently you can set access levels, but these settings do not yet effectively limit any access on the site
5.3 | Creating usernames and passwords for all Vendors 20% COMPLETE |  |  |  | All current Vendors will automatically have a username and password generated and emailed to them, or they will have an ability to set the aforementioned. Should they forget their credentials, there will be a secure way for them to retrieve their credentials.
a | credentials created or ability for vendor to create their own |  |  |  | not yet created
b | ability for admin to manually change login password |  |  |  | ok
5.4 | Creating usernames and passwords for all Clients 20% COMPLETE |  |  |  | All current Greek Organizations will automatically have a username and password generated and emailed to them, or they will have an ability to set the aforementioned. Should they forget their credentials, there will be a secure way for them to retrieve their credentials.
a | credentials created or ability for client to create their own |  |  |  | not yet created
b | ability for admin to manually change login password |  |  |  | ok
Phase 3 Work - Updates to GreekLicensing.com
6.1 | Updating layout and design 80% COMPLETE |  |  |  | All functionality included in the existing GreekLicensing.com will be included in the final outcome, including but not limited to, AMC advertising banners, newsfeeds, and a sophisticated vendor search interface allowing consumers to identified licensed vendors by name, product and/or location.
a | Creation of a new, updated branding for greeklicensing.com |  |  |  | ok - branding updated via new wordpress site
b | All greek orgs have a searchable roster |  |  |  | the roster exists but there are some bugs with the search filters | Fixed
c | ability to set advertising banners per organization |  |  |  | admin can set banners, but there needs to be a away to set the 'activity date' so that banners are automatically taken down | Fixed
6.2 | Vendor Web Profiles 40% COMPLETE |  |  |  | Vendors will be able to submit changes to content on their publically-viewable web profiles, including company description, vendor logo, and 10 product images. Additional product image 'slots' may be granted by the admin. All requested changes are placed in a queue for the admin to approve or reject, side-by-side with the current profile version. Any admin-typed approvals or rejections should be emailed to vendor upon submission. Any vendor-requested updates to their private contact information should be granted automatically; old versions of contact information should be auto-achieved for Admin viewing.
a | every vendor has a place in their profile to customize their public 'web profile' |  |  |  | ok
b | vendor can request changes to web profile |  |  |  | ok - but vendor cannot upload promotional product images | Fixed
c | admin can review requested changes in a queue - and toggle between old and newly proposed versions |  |  |  | The toggle between old and new verisons does not work. Also the company name field is deleted and logo is not viewable on the powers.softura.com version | Jace wants an example
d | admin can reject changes - accompanied by a notification email |  |  |  | admin can reject, but no email is sent | Fixed
e | admin can approve changes - accompanied by a notificaiton email |  |  |  | admin can approve, but no email is sent | Fixed
f | vendor logo's and content are displayed on the public website |  |  |  | content is mostly correct, but there are some logo-sizing, and promotional product image issues still | Fixed
g | vendor promotional product images are capped at 10, but can be expanded by admin |  |  |  | works on devgreeklicensing but not powers.softura.com | Fixed
h | vendor can make updates to their (non-public) contact information, these updates will take effect without Affinity approval, but over-written contact info is auto archived for admin viewing |  |  |  | no archive feature yet exists | Jace feels this can be done after June 20, but he will give estimate by tomorrow.
6.3 | Greek Org Whitelabeled Vendor Rosters 50% COMPLETE |  |  |  | All Greek organizations will have a searchable vendor roster, accessible by the public through greeklicensing.com. Each greek org will have two versions of their search page; the first will be with branding consistent with the GL.com site as a whole. The second will have a customizable banner and font, button, and background colors so as to be able to be placed inside a client's existing website to match Client website branding.
a | All greek orgs have a searchable roster |  |  |  | the roster exists but there are some bugs with the search filters | Fixed
b | each greek org has two urls for the two verisons of their roster page |  |  |  | ok
c | the client-customized version of their vendor roster should be modifiable enough so as to fit within a client's existing website seamlessly |  |  |  | some basic customization exists but it is not nearly modifiable enough so as to look good | Fixed
6.4 (same as 2.2) | Tying database driven pages to the "App" database 100% COMPLETE |  |  |  | All info about Greek Orgs and Vendors should come from the application database. When a vendor association is changed in the AMC admin portal a licensee will appear (and a revoked licensee will disappear) on the public page (and vendor search interface) of GL.com
a | Backend database drives the content on the public webpage www.greeklicensing.com |  |  |  | The framework seems to be in place. Once a change is made to a vendor's status or information, that change appears to be reflected on the public website

## Release 42513
Phase 1 - Fundamental Modules |  | Module | Phase | Status | Description
1.1 | Registration Module |  | Phase 1 |  | Any company may request access to a custom vendor portal page by completing a simple form. Admin will have the ability to review the registration request and either 1) grant them access, creating a new vendor file in the system or 2) reject access because an existing file is already in place. In the event of #2, Admin will be able to set a temporary login credential for the vendor so that they can gain access to their existing database record.
e | declined vendor files are removed | Registration Module | Phase 1 |  | currently these vendor files statuses go from 'pending' to 'cancelled' - which is wrong. The files should be deleted entirely, and only viewable from Admin >registrants>Declined. If they must remain in the system they can be listed as 'Duplicate' status | Fixed
1.2 | Licensing Module 50% COMPLETE |  | Phase 1 |  | The ability to electronically facilitate the signature of our license agreements online. Typed signatures should have font of a signature. Almost all license agreements are templates, and therefore upon and vendor's application, they auto populate for the Admin to review and edit. The workflow is as follows: 1) vendor applies for agreement 2) vendor application auto-populates a license agreement for the admin 3) Admin reviews agreement and auto-attaches product sample images 4) If approved, Admin forwards agreement to vendor for signature 5) When signed by vendor, agreement is forwarded to client for countersignature, Client is able to view product same images 6) Once dually signed, a pdf copy of a properly-formatted agreement is sent to vendor and admin via email 7) a copy of the dually signed agreement is also stored online.
b | admin can preview agreement templates | Licensing Module | Phase 1 |  | preview button used to work, but no longer does | fixed
d | Vendor applies | Licensing Module | Phase 1
e | company info | Licensing Module | Phase 1 |  | state should auto populate | Fixed
f | organizations | Licensing Module | Phase 1 |  | formatting looks a little off (some names go to two lines) | Fixed
h | financials | Licensing Module | Phase 1 |  | ok - auto-populates but red bar at top should be gone | Fixed
k | pay by emailed invoice | Licensing Module | Phase 1 |  | invoice rec'd but need to be formatted, also invoice does not show in vendors invoice tab | Fixed
l | Vendor provides payment | Licensing Module | Phase 1 |  | no ability for vendor to see or pay invoice
m | Vendor sends in product samples/Admin uploads to vendor 'product info tab' | Licensing Module | Phase 1 |  | uploading does not stick | Fixed
n | Vendor's quality sample images auto attach to the pending agreement | Licensing Module | Phase 1 |  | they can be added manually but they do not yet auto attach | Fixed
p | Admin can view and sort agreements that are in the queue in Vendors > Lisc. Agreements | Licensing Module | Phase 1 |  | pending agreements are shown but you can't filter by org or vendor. Also the drop-down is blank. | Fixed
s | Admin can view and preview the agreement | Licensing Module | Phase 1 |  | preview button used to work, but no longer does | Fixed
u | Admin rejects agreement, and sends to vendor | Licensing Module | Phase 1
v | Vendor can view and preview the agreement | Licensing Module | Phase 1 |  | preview button used to work, but no longer does | Fixed
w | Vendor signs and agrees to contract | Licensing Module | Phase 1 |  | title should be below name in the signature field. Font should look more like a signature. | Fixed
x | once vendor signs - agreement status should be 'awaiting client signature' | Licensing Module | Phase 1 |  | the status is correct, but the vendor should not be able to view the agreement under the 'action' tab | Fixed
dd | Client can view and preview the agreement | Licensing Module | Phase 1 |  | preview button used to work, but no longer does. Agreement has lost it's formatting as well. | Fixed
ee | If client rejects, then email is sent to affinity | Licensing Module | Phase 1
gg | the dually signed agreement is viewable from both client, affinity and vendor profiles | Licensing Module | Phase 1 |  | dually signed agreements are not yet viewable by client, and have lost their formatting in both the vendor and admin views. | Fixed
1.4 | Notification Module |  | Phase 1 |  | This is an notification system allowing the Admin to send messages to vendors, via email and/or as a notification to their homepage. All notifications send within this system are recorded in the Vendor's 'correspondence tab' of their respective CRM profile page within the Admin portal.
c | messages can be sent from email and/or site notification | Notification Module | Phase 1 |  | site notifications are posted but emails are not yet sent to either vendors or clients | Fixed
d | messages are copied in the correspondence tab of recipents | Notification Module | Phase 1 |  | messages are copied to a single vendors' correspondence tab, but not yet for clients | Fixed
e | send message for all vendors of a client | Notification Module | Phase 1 |  | messages are posted to each vendor's profile page, but they are not yet copied to the vendors' correspondence tab | Fixed
f | send message for all vendors | Notification Module | Phase 1 |  | messages are posted to each vendor's profile page, but they are not yet copied to the vendors' correspondence tab | Fixed
i | send message for select clients | Notification Module | Phase 1 |  | messages are posted to each client's profile page, but they are not yet copied to the clients' correspondence tab | Fixed
k | vendors can view messages from their profiles | Notification Module | Phase 1 |  | admin is able to post the message, however the message formatting shows the html in the vendor's profile if the vendor is trying to view it | Fixed
m | recipeint can view message when they click on the notification tab link in their profile | Notification Module | Phase 1 |  | small bug - when the preview is clicked nothing happens. If you go to all notificaitons, then click on the message, it does open however. | Fixed
1.6 | Design Module |  | Phase 1 |  | The ability for Vendors to post designs for the Admin's review. The ability for the Admin to approve, reject or deny with comments. All design decisions are both sent to the admin via email with a thumbnail image, and logged in the portal. The ability for the Admin to search and sort designs that were submitted by a particular Vendor, or search and sort designs submitted for a particular Client.
h | admin can search/filter old approved & rejected designs | Design Module | Phase 1 |  | fatal error' occurs when filtering rejected, approved designs | Fixed
i | 'admin can click and view old approved & rejected designs | Design Module | Phase 1 |  | when admin clicks on a thumbnail, the pop up window goes to the top left image | Fixed
Phase 3 Work - Updates to GreekLicensing.com
6.1 | Updating layout and design 80% COMPLETE |  |  |  | All functionality included in the existing GreekLicensing.com will be included in the final outcome, including but not limited to, AMC advertising banners, newsfeeds, and a sophisticated vendor search interface allowing consumers to identified licensed vendors by name, product and/or location.
a | Creation of a new, updated branding for greeklicensing.com |  |  |  | ok - branding updated via new wordpress site
b | All greek orgs have a searchable roster |  |  |  | the roster exists but there are some bugs with the search filters | Fixed
6.2 | Vendor Web Profiles 40% COMPLETE |  |  |  | Vendors will be able to submit changes to content on their publically-viewable web profiles, including company description, vendor logo, and 10 product images. Additional product image 'slots' may be granted by the admin. All requested changes are placed in a queue for the admin to approve or reject, side-by-side with the current profile version. Any admin-typed approvals or rejections should be emailed to vendor upon submission. Any vendor-requested updates to their private contact information should be granted automatically; old versions of contact information should be auto-achieved for Admin viewing.
a | every vendor has a place in their profile to customize their public 'web profile' |  |  |  | ok
b | vendor can request changes to web profile |  |  |  | ok - but vendor cannot upload promotional product images | Fixed
d | admin can reject changes - accompanied by a notification email |  |  |  | admin can reject, but no email is sent | Fixed
e | admin can approve changes - accompanied by a notificaiton email |  |  |  | admin can approve, but no email is sent | Fixed
f | vendor logo's and content are displayed on the public website |  |  |  | content is mostly correct, but there are some logo-sizing, and promotional product image issues still | Fixed
g | vendor promotional product images are capped at 10, but can be expanded by admin |  |  |  | works on devgreeklicensing but not powers.softura.com | Fixed
6.3 | Greek Org Whitelabeled Vendor Rosters 50% COMPLETE |  |  |  | All Greek organizations will have a searchable vendor roster, accessible by the public through greeklicensing.com. Each greek org will have two versions of their search page; the first will be with branding consistent with the GL.com site as a whole. The second will have a customizable banner and font, button, and background colors so as to be able to be placed inside a client's existing website to match Client website branding.
a | All greek orgs have a searchable roster |  |  |  | the roster exists but there are some bugs with the search filters | Fixed
c | the client-customized version of their vendor roster should be modifiable enough so as to fit within a client's existing website seamlessly |  |  |  | some basic customization exists but it is not nearly modifiable enough so as to look good | Fixed