## Sheet1
Status | Issue Name | Notes from Affinity | Screenshare/SharePoint Link | 8/8/2013 Status
Open | Royalty Reporting - Testing Document | Partially fixed - see new version of document for notes. Some bugs are new, most were fixed, some were unaddressed. | http://cp2013.softura.com/greeklicensing/Shared%20Documents/Royalty%20Reporting%20Testing.docx | Completed
Open | Payments/Invoicing - Remove $0 line items | Partially fixed - sometime getting a fatal error | http://screencast.com/t/KuS0ySJ7KH3 | Completed
| Payments/Invoicing - Editing open invoices makes them look paid | FIXED
| Payments/Invoices - After editing an invoice, 'paid in full' doesn't work | FIXED
| Manual Agreements; 'add new license' screen | FIXED
| Adding 'other' Product Information | FIXED
| Sample Product Reciept Status | FIXED - AWESOME WORK FIGURING THIS ONE OUT!
Open | Artwork Module - Feedback Document | Partially fixed - see new version of document for notes | http://cp2013.softura.com/greeklicensing/Shared%20Documents/Artwork%20Testing%20Document.docx | Completed
| Invoicing - edit existing invoices - no way to delete line item | FIXED
| License Application - application invoice not generated in portal | FIXED (invoice needs formatting but that's covered in a separate note)
| Web Profile - Company Name | FIXED
| Web Profile - Promotional Products Deleted | FIXED
Open | Web Profile - logo distortion | Issue still exists | http://screencast.com/t/cFLRIL9zT2 | Completed
| Web Profile - reset company logo to default | CLOSED (but issue was not fixed)
| Bank Information Should Not Display | CLOSED (though you deleted this section, rather than fixing issue)
| Automatic Vendor Status Changes | FIXED
| Web Profile - white labeled version | FIXED
Open | Web profile - rejection email content | Partially fixed - not all notes were addressed | http://screencast.com/t/dQRJve0eGAC | Completed