## Sheet1
Module | Items | Page | Current Status | Expected Date of Delivery
Homepage | HOME PAGE
Homepage | Home | Landing page(Home page) | Completed | 16th May
Homepage | Our Clients | Our-Clients page | Completed | 16th May
Homepage |  | client-Profile page | Completed | 16th May
Homepage |  | vendor-search(search for product(submit)) | Inprogress | 16th May
Homepage |  | Vendor-profile page | Inprogress | 16th May
Homepage | Aboutus | About-us page | Completed | 16th May
Homepage | Find Licensed Products | find-licensed-products | Completed | 16th May
Homepage | Become Licensed vendor | become-a-licensed-vendor page | Completed | 16th May
Homepage |  | Request access to vendor gateway link(signup/index/type/vendor) | Inprogress | 16th May
Homepage | Vendor login | login page | Inprogress | 16th May
Homepage | client login | login page | Inprogress | 16th May
Homepage | Forgot username & pwd | forgot page | Inprogress | 16th May
Homepage | Contact us | Contact page | Inprogress | 16th May
ADMIN LOGIN
Admin-Dashboard | Dashboard | Most recent license page - side banner "affinity consultant" | Not Started | 16th May
Admin-Dashboard | Accout settings | setting page(update setting) | Inprogress | 16th May
Admin-Dashboard | Background jobs | jobs page | Inprogress | 16th May
VENDORS
Admin-Vendor | Dashboard | Vendor listing(search) | Inprogress | 16th May
Admin-Vendor | Search by Category | Search by Contact | Not Started
Admin-Vendor |  | Search by Correspondence | Not Started
Admin-Vendor |  | Search by Opearations | Not Started
Admin-Vendor |  | Search by Clients | Not Started
Admin-Vendor |  | Search by Lisc. Agreements | Not Started
Admin-Vendor |  | Search By action | Not Started
Admin-Vendor |  | Search By Payments | Not Started
Admin-Vendor |  | Search by notes | Not Started
Admin-Vendor |  | Search by invoices | Not Started
Admin-Vendor |  | Search By Docs | Not Started
Admin-Vendor |  | Search By Webprofile | Not Started
Admin-Vendor | Quick Lookup | Quick vendor search | Not Started
Admin-Vendor | Lisc. Agreements | Licenses page list | Not Started
Admin-Vendor |  | License Review | Not Started
Admin-Vendor |  | view financial statement | Not Started
Admin-Vendor |  | View upload license | Not Started
Admin-Vendor |  | Sample add page | Not Started
Admin-Vendor |  | Decline | Not Started
Admin-Vendor |  | Approval (confirmation popup - emailing screen) | Not Started
Admin-Vendor | Designs | Pending Listing | Not Started
Admin-Vendor |  | Approved Listing | Not Started
Admin-Vendor |  | Rejected Listing | Not Started
Admin-Vendor |  | Design review(approve or reject) | Not Started
Admin-Vendor | Royalty Reports | View all reports(get reports) - Lisitng | Not Started
Admin-Vendor |  | Uploading files | Not Started
Admin-Vendor |  | Pending review on grid (Reject or Approve) | Not Started
Admin-Vendor |  | Company name (contact page) | Not Started
Admin-Vendor |  | Vendor contact - view | Not Started
Admin-Vendor |  | Vendor- contact -Add/Edit | Not Started
Admin-Vendor |  | Vendor profile -view | Not Started
Admin-Vendor |  | Vendor profile -Edit | Not Started
Admin-Vendor | Invocies | Invoices listing | Not Started | 16th May
Admin-Vendor |  | Create an invoice page | Inprogress | 16th May
Admin-Vendor |  | Generate late fee invoices | Not Started
Admin-Vendor |  | Generate adv. Payment invoices | Not Started
Admin-Vendor |  | Generate new confirmation page | Not Started
Admin-Vendor |  | send late fee notification(invoice-send-late-fee-notification) | Not Started
Admin-Vendor | Payments | all-Payment(Paymentlisting) | Not Started
Admin-Vendor |  | Payment View | Not Started
Admin-Vendor |  | Payement edit/save/Delete | Not Started
Admin-Vendor |  | Vendor contact - view/edit | Not Started
Admin-Vendor | Add a Vendor | Vendor - Add | Inprogress | 16th May
Admin-Vendor |  | vendor -edit | Inprogress | 16th May
Admin-Vendor |  | Contact- add/edit/view | Inprogress | 16th May
Admin-Vendor | Registrants | Review Listing | Inprogress | 16th May
Admin-Vendor |  | Approved Listing | Inprogress | 16th May
Admin-Vendor |  | Declined listing | Inprogress | 16th May
Admin-Vendor |  | Review registrant page | Inprogress | 16th May
Admin-Vendor |  | View registrants page | Inprogress | 16th May
Admin-Vendor |  | Reason for declining page | Inprogress | 16th May
Admin-Vendor | Web profile Approval | All Listing | Not Started
Admin-Vendor |  | Pending lising | Not Started
Admin-Vendor |  | Approved Listing | Not Started
Admin-Vendor |  | Declined listing | Not Started
Admin-Vendor |  | Company view for all lising | Not Started
Admin-Vendor |  | View current version | Not Started
Admin-Vendor |  | Reason for decling popup | Not Started
CLIENTS
Admin-Clients | Dashboard | Lisitng all clients (alphabetical order) | Inprogress | 16th May
Admin-Clients | Search | search screen- client view | Inprogress | 16th May
Admin-Clients | Search by Category | search by setup | Not Started
Admin-Clients |  | Search by Correspondence | Not Started
Admin-Clients | Licensing Agreements | Lisc-Agreement grid | Not Started
Admin-Clients |  | Client name with applying vendors name listing | Not Started
Admin-Clients |  | Pending review on grid (Reject or Approve) | Not Started
Admin-Clients | Quarterly Payment Reports | Payement report listing | Not Started
Admin-Clients | Master license Template | With insurance | Not Started
Admin-Clients |  | Without insurance | Not Started
Admin-Clients |  | Addendums | Not Started
Admin-Clients |  | Create addendums | Not Started
Admin-Clients | Add a Client | setup page | Inprogress | 16th May
Admin-Clients |  | Legal screen | Inprogress | 16th May
Admin-Clients |  | Operations screen | Inprogress | 16th May
Admin-Clients |  | Royalty screen | Inprogress | 16th May
Admin-Clients |  | Notes screen | Inprogress | 16th May
Admin-Clients |  | Lic. Template screen | Inprogress | 16th May
EVENTS
Admin-Events | Dashboard | Event listing/Search screen | Completed | 16th May
Admin-Events |  | All events | Completed | 16th May
Admin-Events |  | Upcoming event listing | Completed | 16th May
Admin-Events |  | Past event listing | Completed | 16th May
Admin-Events |  | Add new event page | Inprogress | 16th May
Admin-Events |  | View/Edit/Delete Event page | Inprogress | 16th May
NOTIFICATION
Admin-Notification | Dashboard | Notification listing | Completed | 16th May
Admin-Notification | Add/edit notificaiton | Add/Edit/view Add new notification page | Inprogress | 16th May
WEBSITE MANAGEMENT
Admin-Website management | Dashboard | User listing/Search screen | Completed | 16th May
Admin-Website management | Users | Add New user page | Completed | 16th May
Admin-Website management |  | View/Edit User page and delete page | Completed | 16th May
Admin-Website management | Banner Management | Banner listing/Search screen | Not Started
Admin-Website management |  | Add Banners | Not Started
Admin-Website management |  | View/Edit screens and delete | Not Started
Admin-Website management |  | Orgs screen | Not Started
VENDOR LOGIN
Vendor login | Licenses | Listing and search screens | Not Started
Vendor login |  | Review and licensing contracts (signature page) | Not Started
Vendor login |  | Confirmation page for submitting signature(SIGN) | Not Started
Vendor login |  | Signed a licensed agreement confirmation | Not Started
Vendor login |  | License Agreement Detail (VIEW) | Not Started
Vendor login |  | Licensing Application - Company Info page | Not Started
Vendor login |  | Licensing Application - Organization page | Not Started
Vendor login |  | Licensing Application - Proposed Use page | Not Started
Vendor login |  | Licensing Application - Financials page | Not Started
Vendor login |  | Licensing Application - Checkout page | Not Started
Vendor login |  | License submittion - bank account details updations | Not Started
Vendor login |  | Confirmation page for submitting Licenses | Not Started
Vendor login | Profile | Profile view/edit | Not Started
Vendor login |  | Contacts add/view/edit | Not Started
Vendor login |  | Product info screen | Not Started
Vendor login |  | Financial info screen | Not Started
Vendor login |  | Web profile screen | Not Started
Vendor login |  | Add product image screen | Not Started
Vendor login | Designs | Listing desingn by All/Approved/Pending/Rejected | Not Started
Vendor login |  | Sumbit new design screen upload | Not Started
Vendor login | Royalty Reports | Submit report by online filling form page By Fillout report by Sales | Not Started
Vendor login |  | Submit report by online filling form page By Fillout report by Greek org | Not Started
Vendor login |  | Add another Greek org button link | Not Started
Vendor login |  | Upload screen | Not Started
Vendor login | Invocies | Invoices listing/Search screen | Not Started
Vendor login |  | Invoices view screen | Not Started
Vendor login |  | All payment listing | Not Started
Vendor login |  | payment view screen | Not Started
Vendor login |  | Bank information page Add/update | Not Started
Vendor login | Events | Listing ALL/UPCOMING/PAST events screen | Not Started
Vendor login |  | Event Details screen | Not Started
Vendor login | Notification | Listing/search notification | Not Started
Vendor login |  | Notification details screen | Not Started
CLIENT LOGIN
Client Login | Licenses | Licenses agreement overview screen listing/ Search | Not Started
Client Login |  | Licenses agreement details screen | Not Started
Client Login | Profile | Organizaiton info page view mode | Not Started
Client Login |  | Web profile screen view mode | Not Started
Client Login | ArtWork | Manage official artwork screen | Not Started
Client Login |  | Add art work/upload | Not Started
Client Login |  | Usage guides listing (Manage usage guides) | Not Started
Client Login |  | Add Usage guides screen | Not Started
Client Login | Quarterly Payment Reports | Fiscal year quarter report listing | Not Started
Client Login | Events | events listing all/upcoming/past and search | Not Started
Client Login | Notifications | Notificaiton details screen | Not Started
|  | Notification listing/search | Not Started